AUDIT BOOKLET

Statutory Audit

Client: ABC Pvt Ltd

Financial Year: 2025-26

Generated: 26-05-2026 20:26

# Table of Contents

1. Engagement Details

2. Audit Team

3. Task Execution Summary

4. Detailed Task Log

5. Comments & Review Trail

6. Query Sheet

7. Working Papers Index

# 1. Engagement Details

| Field | Details |
| --- | --- |
| Client Name | ABC Pvt Ltd |
| Title | Statutory Audit |
| Type | Statutory Audit |
| Financial Year | 2025-26 |
| Period | 2025-04-01 to 2026-03-31 |
| Status | Active |
| PAN | AAACA1234A |
| GSTIN | 24AAACA1234A24 |
| Prepared by |  |
| Firm Reg. No. |  |

# 2. Audit Team

| Sr. | Name | Role | Email |
| --- | --- | --- | --- |
| 1 | System Administrator | Team Leader | admin@firm.local |
| 2 | Audit Member 1 | Member | m1@firm.local |
| 3 | Team Leader | Team Leader | tl@firm.local |

# 3. Task Execution Summary

| Status | Count |
| --- | --- |
| Pending | 45 |
| Total | 45 |

# 4. Detailed Task Log

| ID | Area | Task | Assigned To | Status | Priority | WP Ref |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Planning | Obtain engagement letter and understand terms of engagement | Audit Member 1, Team Leader | Pending | High | SA 210 |
| 2 | Planning | Understand the entity and its environment including internal controls | System Administrator | Pending | High | SA 315 |
| 3 | Planning | Perform risk assessment procedures and identify significant risks | Audit Member 1, System Administrator | Pending | High | SA 315 |
| 4 | Planning | Determine materiality levels for the audit | Team Leader | Pending | High | SA 320 |
| 5 | Planning | Develop overall audit strategy and detailed audit plan | Unassigned | Pending | High | SA 300 |
| 6 | Cash & Bank | Obtain bank confirmation letters for all bank accounts | Unassigned | Pending | High | SA 505 |
| 7 | Cash & Bank | Verify bank reconciliation statements as at year-end | Unassigned | Pending | High |  |
| 8 | Cash & Bank | Perform cash count and verify cash book balances | Unassigned | Pending | Medium |  |
| 9 | Cash & Bank | Review fixed deposits, interest accrued and TDS thereon | Unassigned | Pending | Medium |  |
| 10 | Trade Receivables | Obtain age-wise analysis of trade receivables | Unassigned | Pending | High |  |
| 11 | Trade Receivables | Send balance confirmation letters to significant debtors | Unassigned | Pending | High | SA 505 |
| 12 | Trade Receivables | Review provision for doubtful debts and write-offs | Unassigned | Pending | High | Ind AS 109 |
| 13 | Trade Receivables | Verify subsequent realisations post year-end | Unassigned | Pending | Medium |  |
| 14 | Inventory | Attend physical stock verification / review management count | Unassigned | Pending | High | SA 501 |
| 15 | Inventory | Verify inventory valuation method (cost or NRV whichever lower) | Unassigned | Pending | High | Ind AS 2 |
| 16 | Inventory | Review slow-moving and obsolete inventory provisions | Unassigned | Pending | Medium |  |
| 17 | Fixed Assets | Verify additions to fixed assets with supporting documents | Unassigned | Pending | High |  |
| 18 | Fixed Assets | Check depreciation calculation as per Companies Act and IT Act | Unassigned | Pending | High | Sch II |
| 19 | Fixed Assets | Verify disposals and impairment assessments | Unassigned | Pending | Medium | Ind AS 36 |
| 20 | Trade Payables | Obtain age-wise analysis of trade payables | Unassigned | Pending | High |  |
| 21 | Trade Payables | Send balance confirmation to significant creditors | Unassigned | Pending | Medium | SA 505 |
| 22 | Trade Payables | Verify MSME dues and interest liability under MSMED Act | Unassigned | Pending | High | MSMED Act |
| 23 | Loans & Borrowings | Verify loan agreements, sanction letters and security details | Unassigned | Pending | High |  |
| 24 | Loans & Borrowings | Check interest calculation and repayment schedule | Unassigned | Pending | Medium |  |
| 25 | Revenue | Verify revenue recognition policy as per applicable standards | Unassigned | Pending | High | Ind AS 115 |
| 26 | Revenue | Perform cut-off testing for revenue transactions around year-end | Unassigned | Pending | High |  |
| 27 | Revenue | Test sales with supporting invoices, delivery challans and POs | Unassigned | Pending | High |  |
| 28 | Expenses | Vouch significant expense items with supporting documentation | Unassigned | Pending | Medium |  |
| 29 | Expenses | Review related party transactions and disclosures | Unassigned | Pending | High | Ind AS 24 |
| 30 | Expenses | Verify employee benefit obligations (gratuity, leave encashment) | Unassigned | Pending | High | Ind AS 19 |
| 31 | Tax | Verify income tax computation and provision for current tax | Unassigned | Pending | High |  |
| 32 | Tax | Review deferred tax asset / liability calculation | Unassigned | Pending | High | Ind AS 12 |
| 33 | Tax | Check GST reconciliation (GSTR-1 vs GSTR-3B vs books) | Unassigned | Pending | High |  |
| 34 | Tax | Verify TDS compliance and reconcile with Form 26AS / AIS | Unassigned | Pending | Medium |  |
| 35 | Statutory Compliance | Check compliance with CARO 2020 reporting requirements | Unassigned | Pending | High | CARO 2020 |
| 36 | Statutory Compliance | Verify compliance with provisions of Companies Act, 2013 | Unassigned | Pending | High | Co. Act 2013 |
| 37 | Statutory Compliance | Review minutes of Board meetings and general meetings | Unassigned | Pending | Medium |  |
| 38 | Financial Statements | Review draft financial statements for completeness | Unassigned | Pending | High |  |
| 39 | Financial Statements | Verify notes to accounts and disclosure requirements | Unassigned | Pending | High |  |
| 40 | Financial Statements | Obtain management representation letter | Unassigned | Pending | High | SA 580 |
| 41 | Completion | Perform subsequent events review | Unassigned | Pending | High | SA 560 |
| 42 | Completion | Evaluate going concern assumption | Unassigned | Pending | High | SA 570 |
| 43 | Completion | Perform analytical review procedures at completion stage | Unassigned | Pending | Medium | SA 520 |
| 44 | Completion | Prepare audit summary memorandum and form audit opinion | Unassigned | Pending | High | SA 700 |
| 45 | Completion | Issue audit report in prescribed format | Unassigned | Pending | High | SA 700/705/706 |

# 5. Comments & Review Trail

# 6. Query Sheet

| Sr. | Query | Response | Status | Raised By | Date | Task Ref |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Mismatch in Opening Trial Balance | Pending | Open | System Administrator | 2026-05-26 | Task 3 Opening verification |

# 7. Working Papers Index

| Sr. | WP Reference | Task | Area | Status |
| --- | --- | --- | --- | --- |
| 1 | SA 210 | Obtain engagement letter and understand terms of engagement | Planning | Pending |
| 2 | SA 315 | Understand the entity and its environment including internal controls | Planning | Pending |
| 3 | SA 315 | Perform risk assessment procedures and identify significant risks | Planning | Pending |
| 4 | SA 320 | Determine materiality levels for the audit | Planning | Pending |
| 5 | SA 300 | Develop overall audit strategy and detailed audit plan | Planning | Pending |
| 6 | SA 505 | Obtain bank confirmation letters for all bank accounts | Cash & Bank | Pending |
| 11 | SA 505 | Send balance confirmation letters to significant debtors | Trade Receivables | Pending |
| 12 | Ind AS 109 | Review provision for doubtful debts and write-offs | Trade Receivables | Pending |
| 14 | SA 501 | Attend physical stock verification / review management count | Inventory | Pending |
| 15 | Ind AS 2 | Verify inventory valuation method (cost or NRV whichever lower) | Inventory | Pending |
| 18 | Sch II | Check depreciation calculation as per Companies Act and IT Act | Fixed Assets | Pending |
| 19 | Ind AS 36 | Verify disposals and impairment assessments | Fixed Assets | Pending |
| 21 | SA 505 | Send balance confirmation to significant creditors | Trade Payables | Pending |
| 22 | MSMED Act | Verify MSME dues and interest liability under MSMED Act | Trade Payables | Pending |
| 25 | Ind AS 115 | Verify revenue recognition policy as per applicable standards | Revenue | Pending |
| 29 | Ind AS 24 | Review related party transactions and disclosures | Expenses | Pending |
| 30 | Ind AS 19 | Verify employee benefit obligations (gratuity, leave encashment) | Expenses | Pending |
| 32 | Ind AS 12 | Review deferred tax asset / liability calculation | Tax | Pending |
| 35 | CARO 2020 | Check compliance with CARO 2020 reporting requirements | Statutory Compliance | Pending |
| 36 | Co. Act 2013 | Verify compliance with provisions of Companies Act, 2013 | Statutory Compliance | Pending |
| 40 | SA 580 | Obtain management representation letter | Financial Statements | Pending |
| 41 | SA 560 | Perform subsequent events review | Completion | Pending |
| 42 | SA 570 | Evaluate going concern assumption | Completion | Pending |
| 43 | SA 520 | Perform analytical review procedures at completion stage | Completion | Pending |
| 44 | SA 700 | Prepare audit summary memorandum and form audit opinion | Completion | Pending |
| 45 | SA 700/705/706 | Issue audit report in prescribed format | Completion | Pending |

Generated: 26-05-2026 20:26